## Sheet1
Date | Day | Backend (Dev 1 & Dev 2) | Front-End (Dev 3 & Dev 4)
2001-06-01 | Mon | Project Setup: Create the base OOP classes (Artifact, Visitor, Guide). Write the C# database connection string. | UI Skeleton: Create the project. Build the Main Menu dashboard shell and create empty forms for Artifacts and Visitors.
2002-06-01 | Tue | Development Paused | Development Paused
2003-06-01 | Wed | Development Paused | Development Paused
2004-06-01 | Thu | Core CRUD: Write the C# methods to INSERT, SELECT, UPDATE, and DELETE artifacts in the database. | Form Design: Design the "Add/Edit Artifact" screen (textboxes, dropdowns). Design the "Register Visitor" screen.
2005-06-01 | Fri | Relationships: Write the SQL/C# logic to link Visitors to Guides (handling relational data). | Fake Data Integration: Add fake, hardcoded data into the UI grids/lists to test layout and data flow.
2006-06-01 | Sat | Development Paused | Development Paused
2007-06-01 | Sun | Unique Feature Backend (QR Logic): Install the QRCoder NuGet package. Write the C# logic to extract specific visitor details from the database and format them into the single string payload needed for generation. Dev 4 can leverage GitHub Copilot within VS Code to quickly generate the boilerplate syntax for the QRCoder library. | Unique Feature UI (QR Display): Add a PictureBox control to the Visitor Dashboard. Wire up the backend to convert the generated QR payload into a Bitmap image and display it on screen. Add an optional "Save Ticket" button.
2008-06-01 | Mon | Dashboard Metrics: Write the SQL queries that calculate total visitors, total artifacts, and available guides. | Dashboard UI: Design the home screen metrics and link them to the backend queries created by Dev 1 & 2.
2009-06-01 | Tue | The First Wire-Up: Devs 1 & 2 sit with Devs 3 & 4. Connect the UI "Save" buttons to the backend C# methods for Artifacts and Visitors. And on the Database side ensure data passes correctly from the UI forms into the database. (+ disscuss any other additions to the backend and the frontend itself)
2010-06-01 | Wed
2011-06-01 | Thu | Exception Handling: Wrap all database calls, QR generation methods, and user inputs in try-catch blocks to prevent the app from crashing. | Input Validation: Add rules to the forms (e.g., preventing users from typing letters into a "Phone Number" or "Age" text box).
2012-06-01 | Fri | Bug Fixing Sprint: Fix the errors found by your QA team. Refine database interactions. | UI Polish: Ensure all buttons align, colors match, and navigation between screens is smooth and logical. Test the QR code scanning directly from the screen.
2013-06-01 | Sat | Final Integration Test: Run through every single feature of the app end-to-end to ensure the database updates correctly and the UI remains responsive. | Final Integration Test: Confirm the unique feature functions flawlessly as an interactive element.
2014-06-01 | Sun | Code Freeze: No new features allowed. Add code comments and package the ZIP archive containing all source code to ensure it is under the 50MB limit. | Code Freeze: Final review of the interactive application elements.