## Sheet1
Activity | Predecessor | Duration | 1st week |  |  |  |  | 2nd Week |  |  |  |  | - Yashod
|  |  | M | T | F | S | S | M | T | F | S | S | - Thinada
Setup | - | 1 | [10 empty] | - Both | bar: 1st week M
CRUD and Relationships | Setup | 3 | bar: 1st week T to 1st week S
QR Logic | - | 2 | bar: 1st week S to 2nd Week M
DashBoard Metrics | CRUD, Relationships | 2 | bar: 1st week S to 2nd Week M
Exception Handling and Bugs Fixing | ALL above | 3 | bar: 2nd Week T to 2nd Week S
Final Integration | ALL above | 1 | bar: 2nd Week S
Activity | Predecessor | Duration | 1st week M: 1st week; 2nd Week M: 2nd Week | - Sandika
|  |  | M | T | F | S | S | M | T | F | S | S | - Hemanga
UI Skeleton | - | 1 | [10 empty] | - Both | bar: 1st week M
Form Design | UI Skeleton | 2 | bar: 1st week T to 1st week F
Fake Data Integration | - | 2 | bar: 1st week M to 1st week T
QR Display | UI Skeleton, Form Design | 3 | bar: 1st week S to 2nd Week M
DashBoard UI | UI Skeleton, Form Design | 4 | bar: 1st week F to 2nd Week M
Input Validation and UI Polish | ALL above | 3 | bar: 2nd Week T to 2nd Week S
Final Integration | ALL above | 1 | bar: 2nd Week S